## Project Plan
PROJECT MANAGEMENT PLAN
Project Name: |  |  |  | Digital Transformation Programme
Project Start: |  | 03/03/2025 |  | Project End: |  |  |  | Last Updated: | 05/06/2026
Total Tasks | Completed | In Progress | Overdue | Blocked | % Complete | STATUS SUMMARY
● Not Started |  | ● In Progress |  | ● Completed |  | ● Overdue |  | ● Blocked
| EXPORT GANTT CHART |  |  | EXPORT DASHBOARD |  |  | EXPORT RAG REPORT
ID | Task Type | Phase | Task / Subtask Description | Planned Start | Planned End | Resource | % Done | Status | Notes / Blockers
| Phase | Phase 1: Project Initiation | Phase 1: Project Initiation | 2025-03-03 | 2025-03-17
1 | Task | Phase 1: Project Initiation | Project Charter Development | 2025-03-03 | 2025-03-07 | James Thornton | 100% | Completed | Approved by Sponsor
2 | Subtask | Phase 1: Project Initiation | ↳ Draft project charter document | 2025-03-10 | 2025-03-11 | James Thornton | 100% | Completed
3 | Subtask | Phase 1: Project Initiation | ↳ Stakeholder review & feedback | 2025-03-10 | 2025-03-11 | George Harris | 100% | Completed
4 | Subtask | Phase 1: Project Initiation | ↳ Final sign-off obtained | 2025-03-10 | 2025-03-10 | Archie Martin | 100% | Completed
5 | Task | Phase 1: Project Initiation | Stakeholder Identification | 2025-03-10 | 2025-03-12 | Sarah Mitchell | 100% | Completed
6 | Subtask | Phase 1: Project Initiation | ↳ Map key stakeholders | 2025-03-13 | 2025-03-13 | Amelia Wilson | 100% | Completed
7 | Subtask | Phase 1: Project Initiation | ↳ Define RACI matrix | 2025-03-13 | 2025-03-14 | James Thornton | 100% | Completed
8 | Task | Phase 1: Project Initiation | Kick-off Meeting | 2025-03-13 | 2025-03-13 | James Thornton | 100% | Completed | All stakeholders attended
9 | Task | Phase 1: Project Initiation | Project Governance Setup | 2025-03-14 | 2025-03-17 | James Thornton | 100% | Completed
| Phase | Phase 2: Requirements Gathering | Phase 2: Requirements Gathering | 2025-03-18 | 2025-04-02
10 | Task | Phase 2: Requirements Gathering | Business Requirements Workshop | 2025-03-18 | 2025-03-20 | Amelia Wilson | 100% | Completed
11 | Subtask | Phase 2: Requirements Gathering | ↳ Facilitated workshop session | 2025-03-21 | 2025-03-21 | Amelia Wilson | 100% | Completed
12 | Subtask | Phase 2: Requirements Gathering | ↳ Document functional requirements | 2025-03-21 | 2025-03-24 | Amelia Wilson | 100% | Completed
13 | Task | Phase 2: Requirements Gathering | Technical Requirements Review | 2025-03-21 | 2025-03-26 | David Patel | 100% | Completed
14 | Subtask | Phase 2: Requirements Gathering | ↳ Architecture feasibility analysis | 2025-03-27 | 2025-03-28 | David Patel | 100% | Completed
15 | Subtask | Phase 2: Requirements Gathering | ↳ Non-functional requirements doc | 2025-03-27 | 2025-03-28 | Emma Clarke | 100% | Completed
16 | Task | Phase 2: Requirements Gathering | Requirements Sign-off Document | 2025-03-27 | 2025-03-28 | George Harris | 100% | Completed | Approved
17 | Task | Phase 2: Requirements Gathering | Gap Analysis Report | 2025-03-31 | 2025-04-02 | Amelia Wilson | 100% | Completed
| Phase | Phase 3: Project Planning | Phase 3: Project Planning | 2025-04-03 | 2025-05-01
18 | Task | Phase 3: Project Planning | Resource Planning | 2025-04-03 | 2025-04-07 | James Thornton | 100% | Completed
19 | Subtask | Phase 3: Project Planning | ↳ Identify resource requirements | 2025-04-08 | 2025-04-08 | James Thornton | 100% | Completed
20 | Subtask | Phase 3: Project Planning | ↳ Confirm resource availability | 2025-04-08 | 2025-04-09 | Sarah Mitchell | 100% | Completed
21 | Task | Phase 3: Project Planning | Risk Assessment & Register | 2025-04-08 | 2025-04-11 | James Thornton | 100% | Completed
22 | Subtask | Phase 3: Project Planning | ↳ Risk identification workshops | 2025-04-14 | 2025-04-15 | Amelia Wilson | 100% | Completed
23 | Subtask | Phase 3: Project Planning | ↳ Risk scoring & mitigation plans | 2025-04-14 | 2025-04-15 | James Thornton | 100% | Completed
24 | Task | Phase 3: Project Planning | Project Schedule Development | 2025-04-14 | 2025-04-22 | James Thornton | 100% | Completed | Baselined
25 | Task | Phase 3: Project Planning | Budget Planning & Approval | 2025-04-23 | 2025-04-25 | Archie Martin | 100% | Completed | Budget approved £250k
26 | Task | Phase 3: Project Planning | Communication Plan | 2025-04-28 | 2025-04-29 | Sarah Mitchell | 100% | Completed
27 | Task | Phase 3: Project Planning | Quality Management Plan | 2025-04-30 | 2025-05-01 | Sophie Bennett | 100% | Completed
| Phase | Phase 4: Design | Phase 4: Design | 2025-05-02 | 2025-06-09
28 | Task | Phase 4: Design | System Architecture Design | 2025-05-02 | 2025-05-14 | David Patel | 100% | Completed
29 | Subtask | Phase 4: Design | ↳ High-level architecture diagram | 2025-05-15 | 2025-05-19 | David Patel | 100% | Completed
30 | Subtask | Phase 4: Design | ↳ Component design specification | 2025-05-15 | 2025-05-19 | Emma Clarke | 100% | Completed
31 | Subtask | Phase 4: Design | ↳ API design documentation | 2025-05-15 | 2025-05-16 | David Patel | 100% | Completed
32 | Task | Phase 4: Design | UX / UI Design | 2025-05-15 | 2025-05-29 | Charlotte Davies | 100% | Completed
33 | Subtask | Phase 4: Design | ↳ User journey mapping | 2025-05-30 | 2025-06-03 | Charlotte Davies | 100% | Completed
34 | Subtask | Phase 4: Design | ↳ Wireframe development | 2025-05-30 | 2025-06-04 | Charlotte Davies | 100% | Completed
35 | Subtask | Phase 4: Design | ↳ High-fidelity mockups | 2025-05-30 | 2025-06-03 | Noah Thompson | 100% | Completed
36 | Task | Phase 4: Design | Database Schema Design | 2025-05-30 | 2025-06-05 | Emma Clarke | 100% | Completed
37 | Task | Phase 4: Design | Design Review & Approval | 2025-06-06 | 2025-06-09 | George Harris | 100% | Completed
| Phase | Phase 5: Development – Core | Phase 5: Development – Core | 2025-06-10 | 2025-07-21
38 | Task | Phase 5: Development – Core | Development Environment Setup | 2025-06-10 | 2025-06-12 | Isla Roberts | 100% | Completed | CI/CD pipelines configured
39 | Subtask | Phase 5: Development – Core | ↳ Repository & branching strategy | 2025-06-13 | 2025-06-13 | David Patel | 100% | Completed
40 | Subtask | Phase 5: Development – Core | ↳ Dev/staging/prod environments | 2025-06-13 | 2025-06-16 | Isla Roberts | 100% | Completed
41 | Task | Phase 5: Development – Core | Core Authentication Module | 2025-06-13 | 2025-06-24 | David Patel | 100% | Completed
42 | Subtask | Phase 5: Development – Core | ↳ User login & registration | 2025-06-25 | 2025-06-30 | David Patel | 100% | Completed
43 | Subtask | Phase 5: Development – Core | ↳ Role-based access control | 2025-06-25 | 2025-06-30 | Emma Clarke | 100% | Completed
44 | Task | Phase 5: Development – Core | Database Implementation | 2025-06-25 | 2025-07-02 | Emma Clarke | 100% | Completed
45 | Task | Phase 5: Development – Core | Core API Layer Development | 2025-07-03 | 2025-07-16 | David Patel | 70% | In Progress | On track
46 | Subtask | Phase 5: Development – Core | ↳ REST endpoints – CRUD operations | 2025-07-17 | 2025-07-23 | David Patel | 100% | Completed
47 | Subtask | Phase 5: Development – Core | ↳ Error handling & logging | 2025-07-17 | 2025-07-21 | Emma Clarke | 50% | In Progress
48 | Subtask | Phase 5: Development – Core | ↳ Unit test coverage | 2025-07-17 | 2025-07-18 | Liam Foster | 0% | Not Started | Awaiting API completion
49 | Task | Phase 5: Development – Core | Code Review – Core Modules | 2025-07-17 | 2025-07-21 | David Patel | 0% | Not Started
| Phase | Phase 6: Development – Features | Phase 6: Development – Features | 2025-07-24 | 2025-09-10
50 | Task | Phase 6: Development – Features | Feature A: Dashboard Module | 2025-07-24 | 2025-08-06 | Emma Clarke | 60% | In Progress
51 | Subtask | Phase 6: Development – Features | ↳ Dashboard data aggregation | 2025-08-07 | 2025-08-12 | Emma Clarke | 80% | In Progress
52 | Subtask | Phase 6: Development – Features | ↳ Dashboard UI components | 2025-08-07 | 2025-08-12 | Noah Thompson | 50% | In Progress
53 | Subtask | Phase 6: Development – Features | ↳ Dashboard real-time updates | 2025-08-07 | 2025-08-08 | David Patel | 0% | Not Started
54 | Task | Phase 6: Development – Features | Feature B: Reporting Engine | 2025-08-07 | 2025-08-18 | Liam Foster | 30% | In Progress | Slight delay – resource conflict
55 | Subtask | Phase 6: Development – Features | ↳ Report template framework | 2025-08-19 | 2025-08-22 | Liam Foster | 50% | In Progress
56 | Subtask | Phase 6: Development – Features | ↳ PDF/Excel export functionality | 2025-08-19 | 2025-08-22 | Liam Foster | 0% | Not Started
57 | Task | Phase 6: Development – Features | Feature C: Notifications System | 2025-08-19 | 2025-08-27 | Emma Clarke | 0% | Not Started
58 | Subtask | Phase 6: Development – Features | ↳ Email notification templates | 2025-08-28 | 2025-09-01 | Emma Clarke | 0% | Not Started
59 | Subtask | Phase 6: Development – Features | ↳ In-app notification centre | 2025-08-28 | 2025-09-01 | Liam Foster | 0% | Not Started
60 | Task | Phase 6: Development – Features | Feature D: User Management | 2025-08-28 | 2025-09-03 | David Patel | 0% | Not Started
61 | Task | Phase 6: Development – Features | Integration Testing – Features | 2025-09-04 | 2025-09-10 | Sophie Bennett | 0% | Not Started
| Phase | Phase 7: Quality Assurance | Phase 7: Quality Assurance | 2025-09-11 | 2025-10-31
62 | Task | Phase 7: Quality Assurance | Test Plan Development | 2025-09-11 | 2025-09-16 | Sophie Bennett | 50% | In Progress
63 | Subtask | Phase 7: Quality Assurance | ↳ Define test scenarios & cases | 2025-09-17 | 2025-09-18 | Sophie Bennett | 100% | Completed
64 | Subtask | Phase 7: Quality Assurance | ↳ Test environment setup | 2025-09-17 | 2025-09-18 | Oliver Hughes | 50% | In Progress
65 | Task | Phase 7: Quality Assurance | System Testing | 2025-09-17 | 2025-09-30 | Oliver Hughes | 0% | Not Started | Dependent on Dev completion
66 | Subtask | Phase 7: Quality Assurance | ↳ Functional system testing | 2025-10-01 | 2025-10-07 | Oliver Hughes | 0% | Not Started
67 | Subtask | Phase 7: Quality Assurance | ↳ Regression test suite | 2025-10-01 | 2025-10-03 | Sophie Bennett | 0% | Not Started
68 | Subtask | Phase 7: Quality Assurance | ↳ Accessibility testing | 2025-10-01 | 2025-10-02 | Oliver Hughes | 0% | Not Started
69 | Task | Phase 7: Quality Assurance | User Acceptance Testing | 2025-10-01 | 2025-10-14 | George Harris | 0% | Not Started | Stakeholders to participate
70 | Subtask | Phase 7: Quality Assurance | ↳ UAT test scripts preparation | 2025-10-15 | 2025-10-17 | Amelia Wilson | 0% | Not Started
71 | Subtask | Phase 7: Quality Assurance | ↳ UAT execution | 2025-10-15 | 2025-10-21 | George Harris | 0% | Not Started
72 | Subtask | Phase 7: Quality Assurance | ↳ UAT sign-off | 2025-10-15 | 2025-10-16 | George Harris | 0% | Not Started
73 | Task | Phase 7: Quality Assurance | Bug Triage & Resolution | 2025-10-15 | 2025-10-24 | David Patel | 0% | Not Started
74 | Task | Phase 7: Quality Assurance | Performance Testing | 2025-10-27 | 2025-10-31 | Oliver Hughes | 0% | Not Started | Load & stress testing
| Phase | Phase 8: Security & Integration | Phase 8: Security & Integration | 2025-11-03 | 2025-12-01
75 | Task | Phase 8: Security & Integration | Security Audit | 2025-11-03 | 2025-11-07 | Henry Walker | 0% | Not Started | External pen test booked
76 | Subtask | Phase 8: Security & Integration | ↳ Vulnerability scanning | 2025-11-10 | 2025-11-11 | Henry Walker | 0% | Not Started
77 | Subtask | Phase 8: Security & Integration | ↳ Penetration testing | 2025-11-10 | 2025-11-11 | Henry Walker | 0% | Not Started
78 | Subtask | Phase 8: Security & Integration | ↳ Security remediation | 2025-11-10 | 2025-11-10 | David Patel | 0% | Not Started
79 | Task | Phase 8: Security & Integration | Third-party Integration | 2025-11-10 | 2025-11-17 | David Patel | 0% | Not Started | CRM & ERP connectors
80 | Subtask | Phase 8: Security & Integration | ↳ CRM API integration | 2025-11-18 | 2025-11-20 | David Patel | 0% | Not Started
81 | Subtask | Phase 8: Security & Integration | ↳ ERP data sync | 2025-11-18 | 2025-11-20 | Emma Clarke | 0% | Not Started
82 | Task | Phase 8: Security & Integration | End-to-End Integration Testing | 2025-11-18 | 2025-11-24 | Sophie Bennett | 0% | Not Started
83 | Task | Phase 8: Security & Integration | Data Migration & Validation | 2025-11-25 | 2025-12-01 | Amelia Wilson | 0% | Not Started | Legacy data migration plan
84 | Subtask | Phase 8: Security & Integration | ↳ Data mapping specification | 2025-12-02 | 2025-12-03 | Amelia Wilson | 0% | Not Started
85 | Subtask | Phase 8: Security & Integration | ↳ Migration dry-run & validation | 2025-12-02 | 2025-12-04 | Isla Roberts | 0% | Not Started
| Phase | Phase 9: Infrastructure & Deployment Prep | Phase 9: Infrastructure & Deployment Prep | 2025-12-05 | 2026-01-08
86 | Task | Phase 9: Infrastructure & Deployment Prep | Production Infrastructure Setup | 2025-12-05 | 2025-12-16 | Isla Roberts | 0% | Not Started | Cloud provisioning required
87 | Subtask | Phase 9: Infrastructure & Deployment Prep | ↳ Cloud environment provisioning | 2025-12-17 | 2025-12-19 | Isla Roberts | 0% | Not Started
88 | Subtask | Phase 9: Infrastructure & Deployment Prep | ↳ Network & firewall configuration | 2025-12-17 | 2025-12-18 | Isla Roberts | 0% | Not Started
89 | Subtask | Phase 9: Infrastructure & Deployment Prep | ↳ Monitoring & alerting setup | 2025-12-17 | 2025-12-19 | Isla Roberts | 0% | Not Started
90 | Task | Phase 9: Infrastructure & Deployment Prep | Deployment Pipeline Automation | 2025-12-17 | 2025-12-23 | Isla Roberts | 0% | Not Started
91 | Task | Phase 9: Infrastructure & Deployment Prep | Disaster Recovery & Backup Plan | 2025-12-24 | 2025-12-31 | Isla Roberts | 0% | Not Started
92 | Subtask | Phase 9: Infrastructure & Deployment Prep | ↳ Backup procedures documentation | 2026-01-02 | 2026-01-05 | Isla Roberts | 0% | Not Started
93 | Subtask | Phase 9: Infrastructure & Deployment Prep | ↳ DR runbook creation | 2026-01-02 | 2026-01-05 | David Patel | 0% | Not Started
94 | Task | Phase 9: Infrastructure & Deployment Prep | Rollback Plan Development | 2026-01-02 | 2026-01-05 | James Thornton | 0% | Not Started
95 | Task | Phase 9: Infrastructure & Deployment Prep | Go-Live Deployment Checklist | 2026-01-06 | 2026-01-08 | James Thornton | 0% | Not Started
| Phase | Phase 10: Training | Phase 10: Training | 2026-01-09 | 2026-02-03
96 | Task | Phase 10: Training | Training Materials Development | 2026-01-09 | 2026-01-20 | Poppy White | 0% | Not Started
97 | Subtask | Phase 10: Training | ↳ End-user training manuals | 2026-01-21 | 2026-01-23 | Poppy White | 0% | Not Started
98 | Subtask | Phase 10: Training | ↳ System admin guide | 2026-01-21 | 2026-01-22 | David Patel | 0% | Not Started
99 | Subtask | Phase 10: Training | ↳ Video tutorial creation | 2026-01-21 | 2026-01-23 | Poppy White | 0% | Not Started
100 | Task | Phase 10: Training | IT/Admin Team Training | 2026-01-21 | 2026-01-23 | Poppy White | 0% | Not Started
101 | Subtask | Phase 10: Training | ↳ System administration training | 2026-01-26 | 2026-01-27 | Isla Roberts | 0% | Not Started
102 | Subtask | Phase 10: Training | ↳ Helpdesk procedure training | 2026-01-26 | 2026-01-26 | Poppy White | 0% | Not Started
103 | Task | Phase 10: Training | End-User Training Rollout | 2026-01-26 | 2026-01-30 | Poppy White | 0% | Not Started | 3 sessions planned
104 | Subtask | Phase 10: Training | ↳ Training session 1 – Finance | 2026-02-02 | 2026-02-02 | Poppy White | 0% | Not Started
105 | Subtask | Phase 10: Training | ↳ Training session 2 – Operations | 2026-02-02 | 2026-02-02 | Poppy White | 0% | Not Started
106 | Subtask | Phase 10: Training | ↳ Training session 3 – Management | 2026-02-02 | 2026-02-02 | Poppy White | 0% | Not Started
107 | Task | Phase 10: Training | Training Completion & Sign-off | 2026-02-02 | 2026-02-03 | George Harris | 0% | Not Started
| Phase | Phase 11: Go-Live | Phase 11: Go-Live | 2026-02-04 | 2026-02-24
108 | Task | Phase 11: Go-Live | Go / No-Go Decision Meeting | 2026-02-04 | 2026-02-04 | Archie Martin | 0% | Not Started | All leads to attend
109 | Subtask | Phase 11: Go-Live | ↳ Readiness assessment review | 2026-02-05 | 2026-02-05 | James Thornton | 0% | Not Started
110 | Subtask | Phase 11: Go-Live | ↳ Formal go/no-go sign-off | 2026-02-05 | 2026-02-05 | Archie Martin | 0% | Not Started
111 | Task | Phase 11: Go-Live | Production Deployment | 2026-02-05 | 2026-02-06 | Isla Roberts | 0% | Not Started | Scheduled weekend deployment
112 | Subtask | Phase 11: Go-Live | ↳ Pre-deployment checks | 2026-02-09 | 2026-02-09 | Isla Roberts | 0% | Not Started
113 | Subtask | Phase 11: Go-Live | ↳ Deployment execution | 2026-02-09 | 2026-02-09 | Isla Roberts | 0% | Not Started
114 | Subtask | Phase 11: Go-Live | ↳ Smoke testing post-deployment | 2026-02-09 | 2026-02-09 | Sophie Bennett | 0% | Not Started
115 | Task | Phase 11: Go-Live | Hypercare Support Period | 2026-02-09 | 2026-02-20 | David Patel | 0% | Not Started | 2-week hypercare window
116 | Subtask | Phase 11: Go-Live | ↳ 24/7 on-call support rota | 2026-02-23 | 2026-02-27 | David Patel | 0% | Not Started
117 | Subtask | Phase 11: Go-Live | ↳ Issue triage & resolution | 2026-02-23 | 2026-02-27 | Emma Clarke | 0% | Not Started
118 | Task | Phase 11: Go-Live | Post Go-Live Review | 2026-02-23 | 2026-02-24 | James Thornton | 0% | Not Started
| Phase | Phase 12: Project Closure | Phase 12: Project Closure | 2026-03-02 | 2026-03-23
119 | Task | Phase 12: Project Closure | Lessons Learned Workshop | 2026-03-02 | 2026-03-03 | James Thornton | 0% | Not Started | All team members to contribute
120 | Subtask | Phase 12: Project Closure | ↳ Facilitate lessons learned session | 2026-03-04 | 2026-03-04 | James Thornton | 0% | Not Started
121 | Subtask | Phase 12: Project Closure | ↳ Document and distribute outcomes | 2026-03-04 | 2026-03-04 | Sarah Mitchell | 0% | Not Started
122 | Task | Phase 12: Project Closure | Final Project Documentation | 2026-03-04 | 2026-03-10 | Sarah Mitchell | 0% | Not Started
123 | Subtask | Phase 12: Project Closure | ↳ As-built documentation | 2026-03-11 | 2026-03-12 | David Patel | 0% | Not Started
124 | Subtask | Phase 12: Project Closure | ↳ Project archive preparation | 2026-03-11 | 2026-03-12 | Sarah Mitchell | 0% | Not Started
125 | Subtask | Phase 12: Project Closure | ↳ Handover pack assembly | 2026-03-11 | 2026-03-11 | James Thornton | 0% | Not Started
126 | Task | Phase 12: Project Closure | Project Formal Handover | 2026-03-11 | 2026-03-11 | Archie Martin | 0% | Not Started
127 | Task | Phase 12: Project Closure | Budget Reconciliation Report | 2026-03-12 | 2026-03-16 | James Thornton | 0% | Not Started
128 | Task | Phase 12: Project Closure | Project Closure Report Sign-off | 2026-03-17 | 2026-03-18 | Archie Martin | 0% | Not Started
129 | Task | Phase 12: Project Closure | Benefits Realisation Plan Setup | 2026-03-19 | 2026-03-23 | George Harris | 0% | Not Started | Handed to BAU team

## Resources
RESOURCE REGISTER
Name | Department | Role | Email / Contact
James Thornton | PMO | Project Manager | j.thornton@company.com
Sarah Mitchell | PMO | Project Coordinator | s.mitchell@company.com
David Patel | Engineering | Lead Developer | d.patel@company.com
Emma Clarke | Engineering | Senior Developer | e.clarke@company.com
Liam Foster | Engineering | Junior Developer | l.foster@company.com
Sophie Bennett | QA | QA Lead | s.bennett@company.com
Oliver Hughes | QA | QA Engineer | o.hughes@company.com
Charlotte Davies | Design | UX Designer | c.davies@company.com
Noah Thompson | Design | UI Designer | n.thompson@company.com
Amelia Wilson | Business | Business Analyst | a.wilson@company.com
George Harris | Business | Product Owner | g.harris@company.com
Isla Roberts | Infrastructure | DevOps Engineer | i.roberts@company.com
Henry Walker | Security | Security Analyst | h.walker@company.com
Poppy White | Training | Training Manager | p.white@company.com
Archie Martin | Stakeholders | Executive Sponsor | a.martin@company.com

## Holidays
UK PUBLIC HOLIDAYS CALENDAR
⚠ Holiday dates in column B are used by VBA macros to auto-adjust task dates. Leave the Resource column blank for public holidays (applies to everyone). Add resource name for individual leave.
Holiday / Leave Name | Start Date | End Date | Resource (blank = all) | Notes
── 2025 Public Holidays ──
New Year's Day | 2025-01-01 | 2025-01-01 |  | England & Wales
Good Friday | 2025-04-18 | 2025-04-18 |  | England & Wales
Easter Monday | 2025-04-21 | 2025-04-21 |  | England & Wales
Early May Bank Holiday | 2025-05-05 | 2025-05-05 |  | England & Wales
Spring Bank Holiday | 2025-05-26 | 2025-05-26 |  | England & Wales
Summer Bank Holiday | 2025-08-25 | 2025-08-25 |  | England & Wales
Christmas Day | 2025-12-25 | 2025-12-25 |  | England & Wales
Boxing Day | 2025-12-26 | 2025-12-26 |  | England & Wales
── 2026 Public Holidays ──
New Year's Day | 2026-01-01 | 2026-01-01 |  | England & Wales
Good Friday | 2026-04-03 | 2026-04-03 |  | England & Wales
Easter Monday | 2026-04-06 | 2026-04-06 |  | England & Wales
Early May Bank Holiday | 2026-05-04 | 2026-05-04 |  | England & Wales
Spring Bank Holiday | 2026-05-25 | 2026-05-25 |  | England & Wales
Summer Bank Holiday | 2026-08-31 | 2026-08-31 |  | England & Wales
Christmas Day | 2026-12-25 | 2026-12-25 |  | England & Wales
Boxing Day | 2026-12-26 | 2026-12-26 |  | England & Wales
── 2027 Public Holidays ──
New Year's Day | 2027-01-01 | 2027-01-01 |  | England & Wales
Good Friday | 2027-03-26 | 2027-03-26 |  | England & Wales
Easter Monday | 2027-03-29 | 2027-03-29 |  | England & Wales
Early May Bank Holiday | 2027-05-03 | 2027-05-03 |  | England & Wales
Spring Bank Holiday | 2027-05-31 | 2027-05-31 |  | England & Wales
Summer Bank Holiday | 2027-08-30 | 2027-08-30 |  | England & Wales
Christmas Day | 2027-12-27 | 2027-12-27 |  | England & Wales
Boxing Day | 2027-12-28 | 2027-12-28 |  | England & Wales

## Stakeholders
STAKEHOLDER EMAIL DISTRIBUTION LIST
Name | Email | Type (To/CC/BCC) | Organisation
Archie Martin | a.martin@company.com | To | Executive Team
George Harris | g.harris@company.com | To | Product
James Thornton | j.thornton@company.com | To | PMO
David Patel | d.patel@company.com | CC | Engineering
Sophie Bennett | s.bennett@company.com | CC | QA
Sarah Mitchell | s.mitchell@company.com | CC | PMO
Amelia Wilson | a.wilson@company.com | CC | Business
Board Secretary | board@company.com | BCC | Board